## README
14 Build Sprint Backlog and Implementation Roadmap
Workbook Purpose | This workbook is the next engineering artifact after the handoff index. It translates the locked EP Design Sheet system into a prioritized build backlog, sprint roadmap, dependencies, acceptance criteria, risks, RACI ownership, and release checklist.
Build Scope | MS 365 / Copilot app architecture for EP Design Sheet: intake, routing, interview modules, scoring, clause triggers, attorney confirmation, drafting handoff, QC, and output generation.
Locked Legal Rules | Scores recommend but do not finalize; Layer 4 attorney confirmation is mandatory; EP-AIP.0/.1/.2 do not include MAPT; MAPT routes to EP-APP; legacy clause names are metadata only.
How Engineer Should Use | Use this as the implementation workplan after reviewing artifacts 00-13 and 12A-12T. Backlog IDs are stable references for project management tickets.
Version | v1.0
Generated | 2026-05-05

## Sprint Roadmap
Sprint | Phase | Primary Objective | Major Deliverables | Exit Criteria | Owner | Target Sequence | Dependencies
Sprint 0 | Foundation | Confirm build environment and artifacts | Dataverse/SharePoint decision, repo/workspace setup, artifact package loaded | Environment and data platform confirmed; artifacts accessible | Engineer + Legal Admin | 0 | 12R, 13
Sprint 1 | Data Layer | Build core tables and option sets | Matter, Client, Family Member, Asset, Priority, Scenario, Clause, Handoff tables; option sets | Tables created with required fields, relationships, validations | Engineer | 1 | 12A, 12B
Sprint 2 | Routing + Intake | Implement intake, family routing, tax posture, senior review gates | Pre-interview review screen, intake screens, routing rules | Sample matters route correctly under 12P tests | Engineer + Associate Attorney | 2 | 12D, 12K, 12P
Sprint 3 | Question Engine | Implement modular interview engine | Module state navigation, question/answer capture, script/POC display, skip logic | Core modules open/close/skip correctly | Engineer | 3 | 12C, 12H, 07, 08
Sprint 4 | Scoring Engine | Implement priority and scenario scoring | P-code scoring, scenario scoring, confidence, exclusions, hard gates | Scores match expected outputs in 12P | Engineer + Senior Attorney | 4 | 12C, 12E, 12P
Sprint 5 | Clause/QC Engine | Implement clause triggers and alerts | Scenario-clause mapping, legacy crosswalk reference, QC alerts, blocker logic | Clause triggers and warnings match 12F/12Q | Engineer + Drafter | 5 | 12F, 12G, 12Q
Sprint 6 | Attorney Confirmation | Implement Layer 4 workflow | Review screen, accept/modify/override, senior review clearance, audit record | No matter can reach drafting-ready without confirmation | Engineer + Attorneys | 6 | 12L, 12M
Sprint 7 | Output Generation | Implement Word/PDF output and handoff | Attorney summary, drafting handoff, homework list, QC report, senior review packet | Outputs merge correct fields and validate required data | Engineer + Paralegal | 7 | 09, 12O
Sprint 8 | UAT + Hardening | Run test cases and fix gaps | 12P test execution, role/security testing, performance checks | All critical test cases pass; open issues logged | Engineer + Legal Team | 8 | 12P, 12M, 12T
Sprint 9 | Pilot Release | Deploy pilot with controlled matters | Pilot users, feedback log, change-control process | Pilot approval; go/no-go decision | Senior Attorney + Engineer | 9 | 12S, 12R, 13

## Backlog Items
Backlog ID | Epic | Feature / User Story | Description | Priority | Sprint | Primary Artifact Source | Acceptance Criteria Reference | Owner | Status | Notes
BL-001 | Data Foundation | Create core Matter table | Create Matter table with plan, scenario, family structure, tax posture, status, review flags, and audit fields. | Critical | Sprint 1 | 12A | AC-001 | Engineer | Not Started | Use controlled option sets; no free-text plan/scenario fields.
BL-002 | Data Foundation | Create Client and Relationship tables | Capture spouses, children, descendants, fiduciaries, beneficiaries, and relationship types. | Critical | Sprint 1 | 12A, 12B | AC-002 | Engineer | Not Started | Relationships must support blended and no-children tracks.
BL-003 | Data Foundation | Load controlled option sets | Implement all locked dropdown values from 12B. | Critical | Sprint 1 | 12B | AC-003 | Engineer | Not Started | Option-set changes require legal approval.
BL-004 | Intake Routing | Build pre-interview checklist screen | Capture tax posture, family type facts, existing documents, assets, and senior-review flags. | Critical | Sprint 2 | 12K | AC-004 | Engineer | Not Started | Must show associate may proceed / senior review required.
BL-005 | Intake Routing | Implement family structure router | Route to unified married, blended, no-children, single, young-family, and APP tracks. | Critical | Sprint 2 | 01, 12D | AC-005 | Engineer | Not Started | Divergence flags must slow down rather than over-branch.
BL-006 | Intake Routing | Implement MAPT/AIP exclusion | If MAPT desired, route to EP-APP and exclude EP-AIP scenarios. | Critical | Sprint 2 | 12D, 12I | AC-006 | Engineer | Not Started | Must surface conflict alert if both selected.
BL-007 | Interview Engine | Build module shell | Display client script, internal POC, questions, required fields, alerts, and next-step logic. | Critical | Sprint 3 | 07, 12H | AC-007 | Engineer | Not Started | POC must be internal-only.
BL-008 | Interview Engine | Implement fiduciary modules | Trustee, POA, ADHC, HIPAA, PR, guardian, disability panel, trust advisor module flow. | High | Sprint 3 | Design Interview, 12H | AC-008 | Engineer + Associate | Not Started | Global fiduciary consistency check required.
BL-009 | Interview Engine | Implement first-death SS-SNT pathway | Forced/conditional/rejected SS-SNT path, skip remarriage after forced selection unless reopened. | Critical | Sprint 3 | Design Interview, 12C, 12H | AC-009 | Engineer + Senior Attorney | Not Started | Most common path must be efficient.
BL-010 | Scoring | Implement P-code priority scoring | Translate client-facing intake answers into internal priorities and ranked profile. | Critical | Sprint 4 | 12C, 12E | AC-010 | Engineer | Not Started | P11 omitted; do not ask Keep Plan Simple.
BL-011 | Scoring | Implement scenario scoring and confidence | Calculate likely plan/scenario and confidence from scoring rules. | Critical | Sprint 4 | 12E | AC-011 | Engineer | Not Started | Scores recommend only.
BL-012 | Scoring | Implement hard gates and exclusions | Hard gates override scoring; exclusions remove inappropriate scenarios. | Critical | Sprint 4 | 12D, 12E | AC-012 | Engineer | Not Started | Tax-3, blended, MAPT/AIP conflicts, disabled beneficiary, firearms, etc.
BL-013 | Clauses | Implement clause trigger engine | Map scenarios/facts to temporary system clause IDs and clause packages. | Critical | Sprint 5 | 12F | AC-013 | Engineer + Drafter | Not Started | Do not use legacy names as logic keys.
BL-014 | Clauses | Expose legacy clause crosswalk | Show former/first-draft clause names as source metadata only. | High | Sprint 5 | 12G | AC-014 | Engineer | Not Started | Placeholder clauses cannot be treated as approved.
BL-015 | QC | Implement alert library | Display exact messages for warnings, blockers, homework, senior-review flags. | Critical | Sprint 5 | 12Q | AC-015 | Engineer | Not Started | Severity must govern drafting-ready status.
BL-016 | Attorney Review | Build confirmation screen | Allow attorney to accept, modify, or override recommendation with reason captured. | Critical | Sprint 6 | 12L | AC-016 | Engineer + Attorneys | Not Started | Mandatory before drafting-ready.
BL-017 | Security | Apply roles and permissions | Implement intake, associate, senior attorney, paralegal, admin, engineer permissions. | Critical | Sprint 6 | 12M | AC-017 | Engineer | Not Started | Paralegal cannot alter confirmed legal design.
BL-018 | Outputs | Generate drafting handoff | Create paralegal drafting handoff using merge field map. | Critical | Sprint 7 | 09, 12O | AC-018 | Engineer + Paralegal | Not Started | Must include final attorney-confirmed plan/scenario and clause list.
BL-019 | Outputs | Generate QC and homework reports | Create client/staff homework, QC report, and senior review packet. | High | Sprint 7 | 10, 12O | AC-019 | Engineer | Not Started | Blocked items must be visible.
BL-020 | Testing | Run expected output test cases | Execute 12P tests across routing, scoring, clauses, QC, and outputs. | Critical | Sprint 8 | 12P | AC-020 | Engineer + Legal Team | Not Started | No critical failures before pilot.
BL-021 | Governance | Version matter outputs | Store system version on matter and output artifacts. | High | Sprint 8 | 12S | AC-021 | Engineer | Not Started | Later rules cannot rewrite old confirmed matters.
BL-022 | Pilot | Deploy pilot release | Pilot controlled matters with feedback loop and change control. | High | Sprint 9 | 12R, 13 | AC-022 | Senior Attorney + Engineer | Not Started | Go/no-go after pilot.

## Milestones
Milestone ID | Milestone | Completion Signal | Dependencies | Responsible Party | Target Sprint | Status
MS-001 | Build environment approved | Dataverse/SharePoint and environments selected | 12R | Engineer + Admin | Sprint 0 | Not Started
MS-002 | Data layer complete | Tables, relationships, fields, and option sets loaded | 12A, 12B | Engineer | Sprint 1 | Not Started
MS-003 | Routing complete | Family routing and senior review gates pass sample matters | 12D, 12K | Engineer + Associate | Sprint 2 | Not Started
MS-004 | Interview engine complete | Modules, scripts, POC, skip logic operating | 12C, 12H | Engineer | Sprint 3 | Not Started
MS-005 | Scoring engine complete | Scenario scores and confidence match expected outputs | 12E, 12P | Engineer + Senior Attorney | Sprint 4 | Not Started
MS-006 | Clause/QC complete | Clause triggers and alerts match mapping specs | 12F, 12G, 12Q | Engineer + Drafter | Sprint 5 | Not Started
MS-007 | Layer 4 complete | Attorney confirmation and overrides fully audited | 12L, 12M | Engineer + Attorneys | Sprint 6 | Not Started
MS-008 | Outputs complete | Word/PDF output templates generate with correct fields | 12O | Engineer + Paralegal | Sprint 7 | Not Started
MS-009 | UAT complete | All critical test cases pass | 12P | Legal Team + Engineer | Sprint 8 | Not Started
MS-010 | Pilot approved | Pilot feedback resolved or accepted for backlog | 13, 12S | Senior Attorney | Sprint 9 | Not Started

## Dependencies
Dependency ID | Upstream Artifact / Item | Downstream Build Area | Dependency Type | Why It Matters | Blocker if Missing? | Notes
DEP-001 | 12A Master Field Data Dictionary | Data Layer | Hard | Tables and fields cannot be built without field definitions. | Yes
DEP-002 | 12B Controlled Option Sets | Forms / Validation | Hard | Dropdowns and validation must use locked values. | Yes
DEP-003 | 12C Question/Answer Scoring Matrix | Interview / Scoring | Hard | Question engine and scoring inputs depend on answer IDs. | Yes
DEP-004 | 12D Routing Rules | Routing | Hard | Family track and senior-review gates must be deterministic. | Yes
DEP-005 | 12E Scoring Engine Rules | Scoring | Hard | Defines how recommendations and confidence are calculated. | Yes
DEP-006 | 12H Module State Machine | Interview Navigation | Hard | Determines module entry, exit, skip, and next-module logic. | Yes
DEP-007 | 12F Scenario-Clause Mapping | Clause Engine | Hard | Scenarios must trigger correct clause concepts. | Yes
DEP-008 | 12G Legacy Clause Crosswalk | Clause Review | Soft | Old names are metadata; helps locate existing draft clauses. | No | Required before final clause approval.
DEP-009 | 12L Attorney Confirmation Workflow | Workflow | Hard | App cannot mark drafting-ready without Layer 4 logic. | Yes
DEP-010 | 12O Merge Field Map | Output Generation | Hard | Word/PDF outputs need exact merge fields. | Yes
DEP-011 | 12P Test Cases | UAT | Hard | Acceptance testing requires expected outputs. | Yes
DEP-012 | 12S Change Management | Governance | Hard | Legal logic cannot be edited informally after launch. | Yes

## Acceptance Criteria
AC ID | Acceptance Criterion | Applies To | Verification Method | Pass / Fail Rule | Related Backlog IDs
AC-001 | Matter table includes required plan, scenario, family, tax, status, review, and audit fields. | Data Layer | Schema review | All critical fields present and locked to option sets where applicable. | BL-001
AC-002 | Client, family, beneficiary, and fiduciary relationships support married, blended, single, no-children, and young-family tracks. | Data Layer | Sample records | All 12P sample matters can be represented without free-text workaround. | BL-002
AC-003 | Controlled option sets are loaded and used for all dropdown fields. | Data Layer / Forms | Form review | No plan, scenario, status, P-code, clause status, or review status is entered as unmanaged free text. | BL-003
AC-004 | Pre-interview screen determines whether associate may proceed or senior review is required. | Routing | Test case execution | TAX-3 and other hard gates block drafting-ready status until cleared. | BL-004
AC-005 | Family structure router assigns correct track and divergence flags. | Routing | 12P tests | All family test cases route to expected script track. | BL-005
AC-006 | MAPT selection excludes EP-AIP scenarios and routes to EP-APP. | Routing / Conflict | Conflict test | App cannot select EP-AIP.0/.1/.2 and MAPT together without conflict alert. | BL-006
AC-007 | Interview module screen displays script, internal POC, questions, capture fields, alerts, and next-step controls. | Interview | UI review | Internal POC not displayed in client-facing output. | BL-007
AC-008 | Fiduciary consistency checks detect minors, inconsistent nominees, missing successor roles, and professional fiduciary needs. | Interview / QC | QC test | All relevant alerts appear under sample cases. | BL-008
AC-009 | Forced SS-SNT path skips remarriage modules unless attorney reopens them. | Interview / First Death | Flow test | Forced path reaches confirmation efficiently and captures trustee follow-up. | BL-009
AC-010 | P-code scoring reflects intake and interview answers without P11. | Scoring | Score test | No P11 appears in tables or user interface. | BL-010
AC-011 | Scenario recommendations and confidence match scoring rules. | Scoring | 12P expected score comparison | Top scenario/confidence matches expected results or flags tie/low confidence. | BL-011
AC-012 | Hard gates and exclusions override scoring. | Scoring / Routing | Negative tests | Excluded scenarios cannot be recommended as final absent attorney override with reason. | BL-012
AC-013 | Clause trigger engine outputs temporary system clause IDs and packages. | Clauses | Clause output test | Legacy names never serve as logic keys. | BL-013
AC-014 | Legacy clause names appear only as source/reference metadata. | Clauses | Record review | Old clause names visible in legacy field only. | BL-014
AC-015 | Alerts use exact message library text and severity logic. | QC | Alert catalog test | Critical blockers prevent drafting-ready status. | BL-015
AC-016 | Attorney confirmation captures accept/modify/override and reason. | Workflow | Audit review | No matter can be drafting-ready without Layer 4 record. | BL-016
AC-017 | Role permissions prevent unauthorized edits and approvals. | Security | Permission test | Paralegal cannot change final legal design; engineer cannot edit legal content in production. | BL-017
AC-018 | Drafting handoff output contains final selected plan, scenario, clauses, fiduciaries, notes, homework, and QC flags. | Outputs | Document review | Output matches 12O merge field map. | BL-018
AC-019 | QC and homework reports separate blockers, review flags, and ordinary homework. | Outputs / QC | Document review | Reports are actionable by staff and attorney. | BL-019
AC-020 | 12P test cases pass before pilot. | Testing | UAT | All critical and high-priority test cases pass or are formally waived. | BL-020
AC-021 | Matter captures system version used for recommendation and final handoff. | Governance | Audit review | Historical matters preserve original logic version. | BL-021
AC-022 | Pilot produces feedback log and go/no-go decision. | Pilot | Pilot review | Senior attorney signs pilot go/no-go decision. | BL-022

## Risks
Risk ID | Risk | Impact | Likelihood | Mitigation | Owner | Status
RISK-001 | Engineer interprets legal prose instead of using locked tables. | High | Medium | Build only from data dictionary, option sets, routing/scoring matrices, and approved artifacts. | Senior Attorney | Open
RISK-002 | Legacy clause names are used as final clause taxonomy. | High | Medium | Use temporary system clause IDs; legacy names metadata only. | Drafter + Engineer | Open
RISK-003 | MAPT/AIP conflict reappears in UI or scoring. | High | Low | Automated exclusion rule and alert message; include in test cases. | Engineer | Open
RISK-004 | Scoring treated as final legal conclusion. | High | Medium | Layer 4 attorney confirmation required for drafting-ready status. | Senior Attorney + Engineer | Open
RISK-005 | Too much POC displayed to clients or in outputs. | Medium | Medium | Mark POC fields internal-only; output templates exclude internal notes unless selected. | Engineer | Open
RISK-006 | Field/options drift after launch. | High | Medium | Use version-control/change-management workflow; legal approval required. | Admin + Senior Attorney | Open
RISK-007 | Output templates omit key drafting information. | High | Medium | Use 12O merge map and validate against 12P test cases. | Paralegal + Engineer | Open
RISK-008 | Roles allow unauthorized legal design changes. | High | Low | Implement 12M permissions and audit rules. | Engineer | Open

## RACI
Workstream | Senior Attorney | Associate Attorney | Paralegal/Drafter | Legal Admin | Engineer | Notes
Data model and option sets | A | C | C | R | R | Legal approval required for option values.
Routing and scoring logic | A | C | I | I | R | Engineer implements; legal team validates.
Interview scripts and POC | A | R | C | I | C | Client-facing and internal-only separation required.
Clause mapping | A | C | R | I | C | Legacy names metadata only.
Attorney confirmation workflow | A | R | C | I | R | Layer 4 mandatory.
Output templates | A | C | R | C | R | Paralegal validates drafting utility.
Security and permissions | A | I | I | C | R | Production changes controlled.
UAT and test cases | A | R | R | C | R | 12P is baseline.
Pilot release | A | R | R | C | R | Senior attorney go/no-go.

## Build Checklist
Checklist ID | Build Check | Required Before | Status | Evidence / Link | Owner | Notes
CHK-001 | All artifacts 00-13 and 12A-12T are accessible to engineer. | Sprint 0 | Not Started |  | Legal Admin
CHK-002 | Data platform decision recorded in implementation log. | Sprint 0 | Not Started |  | Engineer
CHK-003 | Core tables built from 12A data dictionary. | Sprint 1 | Not Started |  | Engineer
CHK-004 | Option sets loaded from 12B. | Sprint 1 | Not Started |  | Engineer
CHK-005 | Routing rules implemented from 12D. | Sprint 2 | Not Started |  | Engineer
CHK-006 | Module state machine implemented from 12H. | Sprint 3 | Not Started |  | Engineer
CHK-007 | Scoring engine tested against 12E and 12P. | Sprint 4 | Not Started |  | Engineer + Legal
CHK-008 | Clause engine and legacy crosswalk implemented from 12F/12G. | Sprint 5 | Not Started |  | Engineer + Drafter
CHK-009 | Layer 4 confirmation workflow implemented from 12L. | Sprint 6 | Not Started |  | Engineer
CHK-010 | Roles and permissions implemented from 12M. | Sprint 6 | Not Started |  | Engineer
CHK-011 | Output templates merged from 12O. | Sprint 7 | Not Started |  | Engineer + Paralegal
CHK-012 | All critical alerts implemented from 12Q. | Sprint 7 | Not Started |  | Engineer
CHK-013 | 12P test cases executed and documented. | Sprint 8 | Not Started |  | Legal Team + Engineer
CHK-014 | Version-control rules implemented from 12S. | Sprint 8 | Not Started |  | Engineer + Admin
CHK-015 | Legal reconciliation checklist passed from 12T. | Before Pilot | Not Started |  | Senior Attorney

## Change Control
Change ID | Date | Artifact / Area | Change Summary | Requested By | Approved By | Status | Version Impact
CHG-001 | 2026-05-05 | 14 Build Sprint Backlog | Initial build backlog and implementation roadmap created. | User | User | Approved | v1.0
CHG-002
CHG-003